## Gantt
Boards - Stream Sense- An Online Video Platform (by months)
|  |  | May-2023 | Jun-2023 | Jun-2023 | Jun-2023 | Jun-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Jul-2023 | Aug-2023 | Aug-2023 | Aug-2023 | Aug-2023 | Sep-2023 | Sep-2023 | Sep-2023 | Sep-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Oct-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Nov-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Dec-2023 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Jan-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Feb-2024 | Mar-2024 | Mar-2024 | Mar-2024
| Start | End | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 4 | 11 | 18
Planning |  |  | 29: Planning
Analysis | 02-Jun-2023 | 04-Jun-2023 | 29: Analysis (02-Jun-23 - 04-Jun-23)
Planning on Tools and Technologies | 05-Jun-2023 | 08-Jun-2023 | 5: Planning on Tools and Technologies (05-Jun-23 - 08-Jun-23)
Requirements Planning | 11-Jun-2023 | 13-Jun-2023 | 5: Requirements Planning (11-Jun-23 - 13-Jun-23); 12: Requirements Planning (11-Jun-23 - 13-Jun-23)
Project Description | 14-Jun-2023 | 16-Jun-2023 | 12: Project Description (14-Jun-23 - 16-Jun-23)
Execution |  |  | 29: Execution
Use case Diagram and Architectural Diagram | 19-Jun-2023 | 19-Jun-2023 | 19: Use case Diagram and Architectural Diagram (19-Jun-23 - 19-Jun-23)
Prelminary Report | 20-Jun-2023 | 25-Jun-2023 | 19: Prelminary Report (20-Jun-23 - 25-Jun-23)
Backend Code Base setup | 26-Jun-2023 | 26-Jun-2023 | 26: Backend Code Base setup (26-Jun-23 - 26-Jun-23)
AWS RDS and S3 setup | 27-Jun-2023 | 27-Jun-2023 | 26: AWS RDS and S3 setup (27-Jun-23 - 27-Jun-23)
MySQL Schema Creation | 28-Jun-2023 | 30-Jun-2023 | 26: MySQL Schema Creation (28-Jun-23 - 30-Jun-23)
Login and registration Backend services | 01-Jul-2023 | 02-Jul-2023 | 26: Login and registration Backend services (01-Jul-23 - 02-Jul-23)
Get Profile data Backend service | 03-Jul-2023 | 04-Jul-2023 | 3: Get Profile data Backend service (03-Jul-23 - 04-Jul-23)
Logout backend service | 05-Jul-2023 | 05-Jul-2023 | 3: Logout backend service (05-Jul-23 - 05-Jul-23)
Set Video Preference backend service | 06-Jul-2023 | 06-Jul-2023 | 3: Set Video Preference backend service (06-Jul-23 - 06-Jul-23)
Get Video Preferences Backend service | 07-Jul-2023 | 07-Jul-2023 | 3: Get Video Preferences Backend service (07-Jul-23 - 07-Jul-23)
Update profile backend service | 08-Jul-2023 | 09-Jul-2023 | 3: Update profile backend service (08-Jul-23 - 09-Jul-23)
Change password backend service | 10-Jul-2023 | 11-Jul-2023 | 10: Change password backend service (10-Jul-23 - 11-Jul-23)
Upload video to service to S3 backend service | 12-Jul-2023 | 13-Jul-2023 | 10: Upload video to service to S3 backend service (12-Jul-23 - 13-Jul-23)
Advance Search algorithm backend service | 13-Jul-2023 | 17-Jul-2023 | 10: Advance Search algorithm backend service (13-Jul-23 - 17-Jul-23); 17: Advance Search algorithm backend service (13-Jul-23 - 17-Jul-23)
Edit Video meta data | 18-Jul-2023 | 18-Jul-2023 | 17: Edit Video meta data (18-Jul-23 - 18-Jul-23)
Delete Video Backend Service | 18-Jul-2023 | 18-Jul-2023 | 17: Delete Video Backend Service (18-Jul-23 - 18-Jul-23)
Preference algorithm service for home page | 19-Jul-2023 | 22-Jul-2023 | 17: Preference algorithm service for home page (19-Jul-23 - 22-Jul-23)
Get my profile videos backend service | 23-Jul-2023 | 24-Jul-2023 | 17: Get my profile videos backend service (23-Jul-23 - 24-Jul-23); 24: Get my profile videos backend service (23-Jul-23 - 24-Jul-23)
OTP service for backend | 25-Jul-2023 | 26-Jul-2023 | 24: OTP service for backend (25-Jul-23 - 26-Jul-23)
Frontend Code base setup | 27-Jul-2023 | 27-Jul-2023 | 24: Frontend Code base setup (27-Jul-23 - 27-Jul-23)
Login Page | 28-Jul-2023 | 29-Jul-2023 | 24: Login Page (28-Jul-23 - 29-Jul-23)
Registration Page | 30-Jul-2023 | 01-Aug-2023 | 24: Registration Page (30-Jul-23 - 01-Aug-23); 31: Registration Page (30-Jul-23 - 01-Aug-23)
Home page | 01-Aug-2023 | 08-Aug-2023 | 31: Home page (01-Aug-23 - 08-Aug-23); 7: Home page (01-Aug-23 - 08-Aug-23)
Set password -forget password | 04-Aug-2023 | 05-Aug-2023 | 31: Set password -forget password (04-Aug-23 - 05-Aug-23)
Forget Password Page | 09-Aug-2023 | 10-Aug-2023 | 7: Forget Password Page (09-Aug-23 - 10-Aug-23)
Video Search Page | 11-Aug-2023 | 14-Aug-2023 | 7: Video Search Page (11-Aug-23 - 14-Aug-23); 14: Video Search Page (11-Aug-23 - 14-Aug-23)
Final Report Template | 12-Aug-2023 | 18-Aug-2023 | 7: Final Report Template (12-Aug-23 - 18-Aug-23); 14: Final Report Template (12-Aug-23 - 18-Aug-23)
Video Play Page | 15-Aug-2023 | 17-Aug-2023 | 14: Video Play Page (15-Aug-23 - 17-Aug-23)
Video Listing page after search | 19-Aug-2023 | 21-Aug-2023 | 14: Video Listing page after search (19-Aug-23 - 21-Aug-23); 21: Video Listing page after search (19-Aug-23 - 21-Aug-23)
Final Report | 20-Aug-2023 | 07-Sep-2023 | 14: Final Report (20-Aug-23 - 07-Sep-23); 21: Final Report (20-Aug-23 - 07-Sep-23); 28: Final Report (20-Aug-23 - 07-Sep-23); 4: Final Report (20-Aug-23 - 07-Sep-23)
Profile Page | 22-Aug-2023 | 24-Aug-2023 | 21: Profile Page (22-Aug-23 - 24-Aug-23)
Video Upload page | 25-Aug-2023 | 27-Aug-2023 | 21: Video Upload page (25-Aug-23 - 27-Aug-23)
Testing entire application | 29-Aug-2023 | 31-Aug-2023 | 28: Testing entire application (29-Aug-23 - 31-Aug-23)